## Reporting
Update Reports

## Task list
| Project Name | <insert project name here>
| Current Task Statuses | Not Started | In Progress | Complete | Overdue
|  | 36.36% | 18.18% | 36.36% | 9.091%
|  | Budget | -19.74
|  | Planned | Actual
|  | 1078.26 | 1098
Tasks | Assigned To | Start | End | Days | Status | Planned Cost | Actual Cost | Notes
Choose Event Time | Stacy Williams | 2021-02-01 | 2021-02-01 | 0 | Complete
Create Guest List | Bozo the Clown | 2021-02-02 | 2021-02-03 | 1 | Complete
Create Invitations | Stacy Williams | 2021-02-03 | 2021-02-07 | 4 | Overdue | 10
Purchase Invitation Gift | Jenny Smith | 2016-02-04 | 2016-02-10 | 6 | In Progress | 250.26 | 300
Send Invitations | Stacy Williams | 2021-02-11 | 2021-02-14 | 3 | Not Started | 10 | 8
Hire Event Coordinator | Bozo the Clown | 2016-02-03 | 2016-02-14 | 11 | Complete | 250 | 200
Plan Event Details | Bozo the Clown | 2016-02-03 | 2016-02-21 | 18 | In Progress
Purchase Required Items | Jenny Smith | 2016-02-21 | 2016-02-28 | 7 | Not started | 258 | 280
Lock in Guest List | Stacy Williams | 2016-03-01 | 2016-03-01 | 0 | Not started
Finalize other Hires | Bozo the Clown | 2016-02-03 | 2016-02-28 | 25 | Complete | 300 | 310
Send Reminders | Stacy Williams | 2016-03-07 | 2016-03-10 | 3 | Not started
PARTY! | Everyone

## Reports (hidden)
| (empty) | (empty)
(empty)
(empty)
Status List
|  |  | Not Started | 4
|  |  | In Progress | 2
|  |  | Complete | 4
|  |  | Overdue | 1

## How to use this template
How to use this template:
ProjectManager.com has created this Excel template to help you generate easy reports with simple-to-update task lists,
budget tracker, workload view and progress tracker in one!
Simply click into the cells you'd like to change to update the data, and the formulas take care of the rest.
Be sure to click the "Update Reports" button on the Reporting tab to re-populate the reports with the changes you've made.
Finally, you should make sure you have "macros enabled" so that the formulas can work properly.
You can find more templates in our Resources section online.
And, of course, if you can update this Excel template, you can manage projects online, too!
Click here to start your free trial at ProjectManager.com: